| Real-Time Safety Alerts App: Network Diagram Key |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS | Activity Symbol | Activity | Duration (Days) | Predecessors |
| 1.1 | 1A | Project Initiation | 1 |  |
| 1.2 | 1B | Identify User Roles | 7 | 1A |
| 1.3 | 1C | Collect Community Stakeholder Requirements | 11 | 1B |
| 1.4 | 1D | Document Emergency Use Cases | 8 | 1C |
| 1.5 | 1E | Create Stakeholder Communication Plan | 3 | 1C |
| 1.6 | 1F | Collect and Refine User Stories | 11 | 1C |
| 1.7 | 1G | Sort Main Features with Stakeholders | 8 | 1F, 1E |
| 1.8 | 1H | Create and Configure Jira Backlog | 4 | 1G |
| 1.9 | 1I | Define High-Availability Feature Criteria | 3 | 1H |
| 2.1 | 2A | Define MVVM Architecture Pattern | 8 | 1I |
| 2.2 | 2B | Define REST API and Azure Web Services | 11 | 2A |
| 2.3 | 2C | Create Native Access Bridge Plan | 7 | 2B |
| 2.4 | 2D | Design High-Availability Data Architecture | 7 | 2B |
| 2.5 | 2E | Document Tech Stack Decisions | 5 | 2B |
| 2.6 | 2F | Create Deployment Guide | 5 | 2C, 2D |
| 2.7 | 2G | Document API Specifications | 5 | 2C, 2D |
| 2.8 | 2H | Create System Architecture Diagrams | 3 | 2E, 2F, 2G |
| 3.1 | 3A | Design Wireframes for Core User Flows | 11 | 2H |
| 3.2 | 3B | Build Interactive Mockups in Figma | 7 | 3A |
| 3.3 | 3C | Create Emergency Interface Designs | 7 | 3A |
| 3.4 | 3D | Develop Cross-Platform UI Components | 7 | 3B, 3C |
| 3.5 | 3E | MILESTONE: Design Approval | 1 | 3D |
| 3.6 | 3F | Conduct Stakeholder Usability Testing | 3 | 3E |
| 3.7 | 3G | Analyze Stakeholder Feedback | 3 | 3F |
| 3.8 | 3H | Iterate UI/UX Based on Reviews | 2 | 3G |
| 3.9 | 3I | Test Interface Under Emergency Conditions | 3 | 3E |
| 4.1 | 4A | Set Up React Native Development Environment | 8 | 3H, 3I |
| 4.2 | 4B | Build Login & Registration Pages | 11 | 4A |
| 4.3 | 4C | Configure Dev & Production Environments | 8 | 4A |
| 4.4 | 4D | Implement Authentication & Security | 12 | 4A |
| 4.5 | 4E | Implement Real-Time Alert Generation | 22 | 4B, 4C, 4D |
| 4.6 | 4F | Create Notification & Alert System | 19 | 4E |
| 4.7 | 4G | Integrate Azure for Syncing & Fallback | 16 | 4F |
| 4.8 | 4H | Develop Offline Emergency Capabilities | 15 | 4G |
| 4.9 | 4I | MILESTONE: Core Functionality Complete | 1 | 4H |
| 4.10 | 4J | Test Low Network Reliability | 7 | 4I |
| 4.11 | 4K | Implement Data Caching & Synchronization | 7 | 4I |
| 4.12 | 4L | Create Connectivity Fallback Mechanisms | 5 | 4J, 4K |
| 4.13 | 4M | Optimize Emergency Response Performance | 4 | 4L |
| 5.1 | 5A | Write Unit & Integration Tests | 11 | 4M |
| 5.2 | 5B | Cross-Platform Compatibility Testing | 11 | 5A |
| 5.3 | 5C | Test Offline Functionality | 7 | 5B |
| 5.4 | 5D | Resolve Performance Issues | 8 | 5C |
| 5.5 | 5E | Set Up CI/CD Pipeline | 3 | 5A |
| 5.6 | 5F | Prepare App Store Submission | 3 | 5D |
| 5.7 | 5G | Configure Monitoring Tools | 3 | 5D |
| 5.8 | 5H | Create Recovery Procedures | 4 | 5F, 5G |
| 5.9 | 5I | Final Acceptance Testing | 4 | 5H |
| 5.10 | 5J | MILESTONE: Project Completion | 1 | 5I |

| Node Key |  |  |
| --- | --- | --- |
| Early Start | Activity Name | Early Finish |
| Late Start | Duration | Late Finish |